User Testing Goals & Process:

Virpets “Resurrection”

First Draft

Prepared by Cheryl Platz

Virpets Lead Interface Designer/User Testing Specialist

Entertainment Technology Center, Carnegie Mellon University

Introduction & Purpose

As a part of a partnership between the Entertainment Technology Center and the Pittsburgh Children’s Museum, our team has been charged with the responsibility of creating an exhibit for eventual inclusion in the new Museum expansion slated to open in 2004.

In order to develop a viable technology-based exhibit, we plan to conduct extensive user tests (also referred to in this document as “playtests” or “guest tests”, due to the context in which they take place) in a decidedly iterative approach to exhibit design. We hope that this approach will open our eyes to the unique needs and desires of our target audience (children between 4 and 8 years of age) – and thus enabling us to create a successful and enjoyable experience.

Target Audience & Inherent Challenges

Ours is a unique challenge – design a technology-heavy interactive museum exhibit for children from 4-7 years of age. A few of the unique challenges that our young user base presents:

- Reading & Writing Ability

    - Most children at this age will not be able to read

    - Those that are literate will not be sophisticated readers.

- Attention Span

    - Children will probably not want to sit through multiple tests.

    - Even if they do, they cannot quantitatively express their preferences.

- Gathering Data

    - It is unlikely that written surveys would be effective in this situation.

    - The best way for us to obtain information is observation and video interview.

- User Consent

    - Parents must give permission for children to appear on video.

    - Our users are not legally capable of providing permission themselves.

As a result, our methodologies will differ somewhat from standard user testing methods. We will not be attempting to gain quantitative knowledge from these tests – rather, we will concentrate on gathering as much from observation as we can. When appropriate (and permissible), we will also tape interviews with the children to get their reactions to the system.

General Conditions

Over the course of the semester, we plan to conduct a minimum of four formal “guest” tests at the Pittsburgh Children’s Museum. Each test will span between 3 and 6 hours, depending upon guest volume and our needs during that particular test. We have no guaranteed location for the tests, but we hope for the first two tests to be in a high-traffic area, and the second two tests to be in a room resembling an auditorium or theatre space. (The experience is being designed with a custom auditorium in mind.)

Every playtest will be run by a minimum of two representatives from the Virpets team. Our User Testing Specialist will be present for every test. Others will be brought on as needed depending on that test’s requirements. One representative from the group will be responsible for videotaping the proceedings and interviewing a subset of participating families. Other Virpets representatives in attendance will be encouraged to take their own observational notes about what they see during the test.

Recruiting Guests

The first two tests will be solicited tests – we will ask museum patrons and their parents if they would like to try out a test exhibit (and thus consent to be videotaped for internal purposes.) We will have release forms available for parents to sign as per standard university procedure, and we will also make available informational flyers that seek to answer any questions parents have about what we are doing and why we’re seeking permission to work with their children. Of course, we will exercise the utmost respect for a family’s wish to privacy – if they are uncomfortable with the videotaping, we will encourage them to enjoy the rest of the museum.

Overall Research Questions:

General

- Are there characters chosen more than other characters?

- What do children take away from the exhibit about puppetry?

- Which methods are most effective for conveying information?

- Would a “mascot” be a valuable tutorial tool?

Creative

- How does a backdrop influence a child’s storytelling capabilities?

- Does a themed set limit their stories to a particular genre?

- What effect does removal of backgrounds have on storytelling?

- How much time do children spend telling stories?

- Are children willing to perform with an unfamiliar child?

Interface

- Is the MS Sidewinder Pro too intimidating as an input device (joystick)?

- Could simple aesthetic changes make the Sidewinder more appealing?

- Is one joystick sufficient?

- How much functionality do kids need to feel in control?

- How much time do kids spend choosing a character?

Technology

- Can we project puppets and scenes from separate computers?

- How durable are the components? (joystick, screen, mouse, touchscreen)

- What abnormal demands will children place on the system?

- How much stress can the system handle?

Proposed Playtesting Schedule

This schedule is subject to change, especially in regards to the subject matter concentrations for each test. This is intended as a rough guide to content creation and materials procurement so that our team will be fully prepared for each of the tests.

Playtest 1: Week of February 20th

High-Level Goals:

- Observe effect of backgrounds on children’s play

- Observe 2-player dynamic

- Test intuitiveness of joystick interaction

- Basic observations about reactions to interaction

Conditions:

- Minimum of 2 puppets in system

- Minimum of 3 worlds (blank, generic, themed)

- Soliciting kids to play in the world (not walk-up and play)

Materials:

- Minimum 2 laptops or desktops/monitors

- Networking equipment (router, cables, etc.)

- 2 joysticks (one per station)

Playtest 2: Mid-March

High-Level Goals:

- Test potential input schemas for puppets

- Test child-facing UI

- Test revisions from Playtests 1&2

Conditions:

- 1-player or 2-player setup

- Solicited play (not walk-up-and play)

- Child-facing UI in place (puppet / world selection as applicable)

Materials

- Minimum of 4 puppets in system

- 2 joysticks per system

- Minimum 1 control computer, 1 server

Playtest 3: Early April

High-Level Goals:

- Test educational value of system

- Observe unfettered play on the system

- Preliminary tests of final system

Conditions:

- 2-player setup

- Full system loop (idle, selection, play)

- Tutorial elements in place

- All completed models to date

Materials:

- Recorder for theStage (if possible)

- 3 computers (Server, 2 control)

- Networking equipment

- All communications software

Playtest 4: Late April/Early May

High-Level Goals:

- Stress-testing final setup

- Enjoyability of final setup

Conditions:

- Setup display area

- Walk-up-and-play (little soliciting)

- All software should be in place

- Most models in place

Materials

- Minimum 3 computers (Server, 2 play stations)

- Large projection screen

- Digital projector

- 2-4 joysticks or other input devices

- Touch Screen displays

Analysis

Much of the knowledge gained from this process will be qualitiative or anecdotal, but it will still be extremely valuable for the team. Tests are scheduled 2 weeks apart to allow for a week of preparation and a week of post-test analysis. Analysis will involve reviewing the video and compiling all team observations, and eventually the preparation of a brief summary of findings after each test. This documentation will hopefully serve as a reference for any motivated changes that are made to the system.